## Ark1
CA PROJECT METHODOLOGY | Gantt Chart |  | Annika Wassmo
Loftus Frukt og Saft - Website |  |  |  |  | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
TASK | TASK | START | END | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
TITLE | OWNER |  |  | IN DAYS | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F | M | T | O | T | F
Project Definition and Planning
Project Management | Project Manager | 1 | 45 | 45
Customer Contact | Project Manager | 1 | 45 | 45
Scope and Goal Setting | Project Manager | 1 | 2 | 2
Kickoff Meeting 1 | Project Manager | 2 | 2 | 1
Proposal | Project Manager | 3 | 3 | 1
Budget | Project Manager | 3 | 3 | 1
Contract | Project Manager | 4 | 4 | 1
Information and Content Gathering
Kickoff Meeting 2 | Project Manager | 5 | 5 | 1
Research | TEAM | 6 | 7 | 2
Design Planning | Front-End Developer | 7 | 8 | 2
Moodboard | Front-End Developer | 8 | 8 | 1
Style Tile | Front-End Developer | 9 | 9 | 1
Wireframes | Front-End Developer | 9 | 10 | 2
UX/UI Design Planning | Front-End Developer | 10 | 10 | 1
High-Fidelity Wireframe | Front-End Developer | 10 | 11 | 2
Coding, Integration and Site Build | Front-End Developer | 12 | 35 | 24
UX/UI Testing | Project Manager | 21 | 35 | 7
Photoshoot - Production | Photographer | 8 | 12 | 5
Photoshoot - Products | Photographer | 13 | 17 | 5
Photoshoot - Owners/Employees | Photographer | 18 | 19 | 2
Photoshoot - Brand | Photographer | 19 | 22 | 4
Photo Editing | Photographer | 23 | 27 | 5
Content Planning | Copywriter | 8 | 9 | 2
Brand History | Copywriter | 9 | 12 | 4
Product Information and Introduction | Copywriter | 13 | 17 | 5
Sales | Copywriter | 18 | 20 | 3
Social Media Present | Digital Marketing Manager | 26 | 35 | 10
Promotion, Advertising and Sales | Digital Marketing Manager | 33 | 39 | 7
Project Launch and Execution
Cross Platform and Browser Testing | Front-End Developer | 36 | 38 | 3
Adjustments and Finalisation | Front-End Developer | 39 | 43 | 5
Handover | Project Manager | 44 | 44 | 1
Launch | Front-End Developer | 45 | 45 | 1